## Sheet1
Subject of Procurement | Insource or Outsource | Type of Sourcing | Justification using Make vs. Buy | RFP or RFQ | Type of Contract Desired
Cloud Hosting & Database Tools | Outsource | Buy (purchase a pre-configured cloud service) | It is more efficient and cost-effective to purchase a proven cloud solution (e.g., AWS, Azure) than to build and maintain in-house infrastructure. | RFQ | Fixed-term subscription/service contract
Specialized UX/UI Consulting | Outsource | Bring in experts (send out for development) | Ade Ventures’ internal team lacks advanced UI/UX design skills needed for a highly user-friendly web portal; external experts can tailor designs to meet best practices. | RFP | Fixed-price contract or Time & Materials contract
Data Migration Services | Outsource | Send out for development | Data migration from legacy systems requires specialized skills and experience making it more viable to contract an expert firm rather than developing in house solutions. | RFP or RFQ | Fixed-price contract
Cybersecurity & Compliance Expertise | Outsource | Bring in experts (consultant services) | High-level cybersecurity expertise is critical but not a core competency of Ade Ventures contracting ensures access to experienced professionals. | RFP | Time & Materials contract with performance milestones
Technical Writing / Training | Outsource | Bring in external resource | Creating clear documentation and effective training materials is essential for successful user adoption, and external specialists are often more efficient at this task. | RFQ | Fixed-price contract for defined deliverables
Software Development Tools & Licenses | Insource | Buy (purchase licenses) | Standard industry tools (IDEs, testing frameworks) must be procured to support the internal development team, buying off the shelf is cost effective. | RFQ | Purchase contract / License agreement
Additional Full-Stack Development Resources (if required) | Outsource | Bring in human resources on a contract basis | If internal capacity is exceeded, it is more efficient to augment the team with external contractors rather than delay the project timeline. | RFP | Time & Materials contract, or Hourly Rate Contract
QA Testing Tools/Software | Insource | Buy (purchase licenses) | Robust testing is necessary for quality assurance. Standard testing software can be purchased and integrated into the development process. | RFQ | Purchase contract