## Sheet1
ID | Activity | Duration (days) | Predecessor | Earliest Start | Earliest Finish
1 | Project Planning & Requirements Gathering | 15 | - | 2025-05-01 | 2025-05-21
1.1 | Conduct stakeholder interviews | 15 | 1 (start) | 2025-05-01 | 2025-05-21
1.2 | Define system requirements | 15 | 1.1 | 2025-05-22 | 2025-06-11
1.3 | Develop project timeline | 10 | 1.2 | 2025-06-12 | 2025-06-25
1.4 | Assign roles & responsibilities | 10 | 1.3 | 2025-06-26 | 2025-07-10
2 | Database & System Development | 25 | 1 | 2025-07-11 | 2025-08-14
2.1 | Design database schema | 25 | 1 (finish) | 2025-07-11 | 2025-08-14
2.2 | Develop inventory mgmt module | 25 | 2.1 | 2025-08-15 | 2025-09-18
2.3 | Implement order processing module | 20 | 2.2 | 2025-09-19 | 2025-10-16
2.4 | Integrate payment processing | 15 | 2.3 | 2025-10-17 | 2025-11-06
3 | Website Development & User Interface Design | 25 | 2 | 2025-11-07 | 2025-12-11
3.1 | Design user interface | 25 | 2.4 | 2025-11-07 | 2025-12-11
3.2 | Develop customer portal | 30 | 3.1 | 2025-12-12 | 2026-01-30
3.3 | Implement admin dashboard | 30 | 3.2 | 2026-02-02 | 2026-03-14
3.4 | Integrate website with database | 25 | 3.3 | 2026-03-17 | 2026-04-20
4 | Security & Compliance Implementation | 15 | 3 | 2026-04-21 | 2026-05-11
4.1 | Implement encryption & authentication | 20 | 3.4 | 2026-04-21 | 2026-05-18
4.2 | Set up role-based access control | 15 | 4.1 | 2026-05-19 | 2026-06-08
4.3 | Ensure compliance with data protection laws | 15 | 4.2 | 2026-06-09 | 2026-06-29
5 | Testing & Quality Assurance | 20 | 4 | 2026-06-30 | 2026-07-27
5.1 | Perform unit testing | 20 | 4.3 | 2026-06-30 | 2026-07-27
5.2 | Conduct integration testing | 20 | 5.1 | 2026-07-28 | 2026-08-24
5.3 | Facilitate UAT | 20 | 5.2 | 2026-08-25 | 2026-09-21
6 | Deployment & User Training | 15 | 5 | 2026-09-22 | 2026-10-12
6.1 | Deploy system to live environment | 15 | 5.3 | 2026-09-22 | 2026-10-12
6.2 | Conduct training for employees & customers | 15 | 6.1 | 2026-10-13 | 2026-11-02
6.3 | Provide user manuals & support materials | 10 | 6.2 | 2026-11-03 | 2026-11-16
7 | Project Closure & Evaluation | 10 | 6 | 2026-11-17 | 2026-11-30
7.1 | Conduct project review meeting | 10 | 6.3 | 2026-11-17 | 2026-11-30
7.2 | Gather stakeholder feedback | 10 | 7.1 | 2026-12-01 | 2026-12-14
7.3 | Document lessons learned | 10 | 7.2 | 2026-12-15 | 2026-12-30