## Master Data
Assumptions & Constraints Log (template)
Project: | add project name here
Project Manager: | add project manager name here
Document Owner: | add document owner name here
Document Creation Date: | add document creation date here
Last Document Change Date: | add last document change date here
Last changed by: | add name of last person who changed the document here
Confidentiality level: | add confidentiality level here if relevant (public use/confidential/secret/...)
Authorized to read: | list stakeholders (groups) authorized to read this document here
Authorized to change (besides the document owner): | list stakeholders (groups) authorized to change this document here
Versioning scheme: | add information regarding document versioning scheme here
Review frequency of document: | add frequency of document reviews here
Master document storage place: | add storage place of master document (source of truth!) here
Approval for new version needed (name): | add information regarding approval process here
Publication procedure for new document version: | add information regarding publication procedure here

## Template Guide & Instructions
Guide to the Assumptions & Constraints Log Template
1. Take key decisions on document management & update sheet "Master Data" accordingly - What is the confidentiality level of the document? Who is authorized to read the document? Does the document have to be password-protected? - Who will be the document owner? Who is authorized to update the document apart from the document owner (if any)? - What is the planned frequency of document reviews & updates? - Where will the document be stored? - How will versions be marked (date in file name or version number in file name or...)? - Do new document versions have to be approved before publication? If yes, by whom? - How will new versions of the document be published and the stakeholder community be informed about a new version?
2. Take decisions on master data for this document & update tab "Ranges" accordingly! - What assumption/constraint status do you want to use in managing the assumptions and constraints? - What categories do you want to use for the assumptions and constraints?
3. Decide if you want to use the simple or advanced version of the assumptions & constraints sheet! - If in doubt start with the simple version. You can change later easily to the advanced version via copy & paste if there is a compelling reason to use the additional columns. Especially at project start the focus should be on managing the constraints and assumptions and not on managing the document! Start simple and stay simple as long as possible!
4. Remove example data from simple or advanced version of the assumptions & constraints sheet!
5. Start populating the simple or advanced sheet: - ID ==> mandatory ==> used to identify an item in the list, but you can use your own ID scheme. To start simple you can count up from one. - type ==> mandatory (valuerange) ==> defines if the item is an assumption or constraint - assumption/constraint ==> mandatory ==> describes the assumption/constraint with a few words (long form description should go into the description field) - status ==> mandatory (value range) ==> should indicate the status of the item (not verified yet/verified as correct/verified as incorrect/...) - category (only in advanced sheet) ==> optional (value range) ==> categorization of assumption/constraint (technical area/project phase/PM area/...) - description ==> optional, but recommended ==> extended description of the item (only in simple sheet: should mention documents and artifacts which are related to the assumption/constraint and might have to be reviewed and updated if there is a change to the assumption/constraint and especially if an assumption has been verified as incorrect!) - related documents & artifacts (only in advanced sheet) ==> optional ==> list of all documents and artifacts that are related to this assumption/constraint and need to be reviewed and updated if there is a change to the assumption/constraint (be as specific as possible, use hyperlinks if possible) - Comments ==> optional ==> any additional information regarding the item, which is not a description - review frequency (only in advanced sheet) ==> optional ==> state if there is a review frequency planned for this particular item which is different than the review frequency of the whole document (weekly/bi-weekly/monthly/quarterly/...) - last review date (only in advanced sheet) ==> optional ==> date of last review if the status and content of the item is still up to date (even if there is no change) - Changed by (only in advanced sheet) ==> optional ==> date of the last change to this item (no matter what of the fields was change) - Change date (only in advanced sheet) ==> optional ==> person who did the last change of this item - Created by (only in advanced sheet) ==> optional ==> date when this item was added to the list initially - Creation date (only in advanced sheet) ==> optional ==> person who created this item
6. Review and update list as stated in the review cycle stated on the master data sheet (or in the column review frequency if you use the advanced sheet)! - Especially if you change an assumption status to "verified as incorrect" you should review the related documents and artifacts accordingly to reflect this. - If you verify an assumption as incorrect or add a constraint which have no effect at all on any document or artifact then that assumption and artifact is actually obsolete.

## Simple AssumptionConstraint She
ID | Type | Assumption/Constraint | Status | Description | Comments
1 | Assumption | Example data: ERP Release 6.1 will be available for public usage on the 1st of December 2014. | verification in process | If ERP release 6.1 is not available by 1st of January 2015 latest, then project has to start with release 6.0 and adapt the project plan via a change request which includes rework the project plan and update of the estimate. Probably this will add two months to the project timeline. | New contact at ERP vendor will be contacted to verify release schedule.
2 | Assumption | Example data: Business analyst Bob Allen will be available for the project 60% of his time (0.6 FTE) during the course of the whole project. | verified as correct | Bob Allen is the most knowledgeable business analyst regarding the new ERP system. If he is not available for at least 60% throughout the whole project, then he has to be replaced by another less skilled BA, which makes it necessary to review and update the BA-related project estimate.lines. | Bob's Manager has confirmed his availability throughout the project (at least 60%, probably up to 80%)
3 | Assumption | Example data: Project reporting will be managed by the division PMO, thus no project-specific project office resource has been budgeted. | verified as incorrect | Project need a project office resource and division PMO has stated that they have sufficient resources available to execute project reporting tasks without additional costs for the project. Thus no project specific project office resource has been budgeted. | Division PMO has no resources available. Thus project office resource has to be budgeted. Budget update not done yet!
4 | Constraint | Example data: Test team will not be available before 1st of July 2015. | not verified yet | Development will be done by end of May 2015 and the project could save some time and idle time, if the test team could start immediately beginning of June 2015. Unfortunately management has mentioned, that the test team is engaged with another project until end of June 2015 and thus only be available beginning of July 2015. | Situation will be verified by project manager with senior management end of Q1/2014!
5 | Constraint | Example data: Lowest cost bidder on PMIS system cannot be used, because company is not on the preferred vendor list. | verified as incorrect | Lowest cost bidder matching the minimum PMIS requirements cannot be selected due to procurement rules (not on preferred vendor list). Thus we have the 2nd bidder, which will increase PMIS related cost by 20%. | Lowest cost bidder has been added to preferred vendor list. Update of project cost estimate in progress (PMIS-related cost drop by 20%)
TEST DATA ENDS HERE (Please remove all previous lines including this before using this sheet!)

## Advanced AssumptionConstraint S
ID | Type | Assumption/Constraint | Status | Category | Description | related docs & elements | Comments | review frequency | last review date | Changed by | Change date | Created by | Creation date
1 | Assumption | Ade Ventures will provide timely feedback and approvals during project review cycles. | Open | Stakeholder Engagement | Delays in feedback may extend the schedule; we assume timely responses to keep tasks on track. | SOW, Project Plan | Critical for schedule adherence; buffer time added. | Monthly | N/A | N/A | N/A | Project Manager | 2025-09-04
2 | Constraint | The project budget is capped at $710K due to the company’s small size (~10 employees). | Open | Financial | Limited funding may restrict hiring or technology acquisitions; scope prioritization is crucial. | Budget Document, SOW | If additional funds are needed, sponsor approval is required. | Monthly | N/A | N/A | N/A | Project Manager | 2025-09-04
3 | Assumption | Existing infrastructure (hardware/network) can support the new system with minimal upgrades. | Open | Technical Infrastructure | If hardware is insufficient, unexpected costs or delays may arise; we assume readiness is adequate. | Infrastructure Audit Report | Must validate early; contingency funds reserved if needed. | Monthly | N/A | N/A | N/A | IT Manager | 2025-09-04
4 | Constraint | The project must be completed within 4–6 months to minimize operational disruption. | Open | Schedule | A tight timeline may increase risk; parallel tasks and phased rollout are planned to meet the deadline. | Gantt Schedule, Project Plan | Aggressive schedule; requires efficient resource allocation. | Bi-weekly | N/A | N/A | N/A | Project Manager | 2025-09-04
5 | Assumption | Key personnel (developers, cybersecurity, QA) will be available as needed or via contracted help. | Open | Resource / Staffing | Unavailability could delay tasks; we assume their availability during critical project phases. | Staffing Plan, RACI Matrix | Backup resources identified; monitor for potential conflicts. | Monthly | N/A | N/A | N/A | Project Manager | 2025-09-04
6 | Assumption | Regulatory requirements remain stable during project execution. | Open | Regulatory / Compliance | Changes could force scope adjustments or rework; we assume no major regulatory shifts mid-project. | Compliance Documents, Industry Standards | Regular monitoring of updates is essential. | Monthly | N/A | N/A | N/A | Compliance Officer | 2025-09-04

## Ranges
Assumption Status Range | Category Range | Type
not verified yet | Category A | Assumption
verification in process | Category B | Constraint
verified as correct | Category C
verified as incorrect