## Overview
Overview
A stakeholder management plan is a significant, success-ensuring artifact to include in your project toolbox and to use during the lifecycle of complex projects. There are many potential stakeholders for a project, such as anyone or any group who may positively or negatively impact the project lifecycle or outcome. A stakeholder is one who may effect, or one who is affected by, the outcome or change. Stakeholders can be internal or external to the organization, having different needs and different levels of involvement. It is important to identify stakeholders and to discern categories to which they belong. Categories of stakeholders include: • Primary stakeholders – those who are directly impacted by the project • Secondary stakeholders – those who are indirectly impacted by the project • Key stakeholders – may be primary or secondary, and are those who have significant influence and/or interest in the project Questions to consider when identifying stakeholders: • To which stakeholder category do they belong? (Primary, Secondary, Key Stakeholder) • What is their interest and influence level? (High/Low) • What is their support level? (Support, Neutral, Against) • What do they need from us? • How do they want to receive information and communications? The stakeholder management plan template is simple, yet useful to document and manage your project stakeholders throughout the project lifecycle. It can be customized by adding or changing column headings to meet the needs of your organization.

## Template
Stakeholder Management Plan
Project Name: Ade Ventures: Digital Transformation for Beverage Distribution |  |  |  |  | Project Manager: Mariam Adegbindin |  |  | Date: 4/23/2025
Who | What |  |  |  | How |  | Who | When | Other
Stakeholder | Stakeholder's Role | Influence High/Low | Interest High/Low | Support Neutral Against | Monitor Inform Satisfy Manage | Strategy | Strategy Owner | Strategy Date | Comments
Project Sponsor (CEO) | Provides funding & strategic direction | High | High | Neutral | Manage | Involve in key decisions. Executive status reports
Project Manager | Lead execution & delivery | High | High | Support | Manage | Daily stand-ups, risk/issue escalations
Business Analyst | Translate needs into requirements | High | High | Support | Manage | Host requirement workshops; maintain traceability matrix
Full-Stack Dev Team | Build core database & web features | Low | High | Support | Inform | Agile sprints with demos and backlog grooming
QA Engineer | Validate quality & functionality | Low | High | Support | Inform | Release test plans & defect reports, UAT coordination
Cybersecurity Specialist | Secure data & compliance | Low | High | Support | Inform | Security reviews, vulnerability scans
Technical Writer/Trainer | Document features & train users | Low | High | Support | Inform | Draft user manuals, schedule training sessions
Internal End Users | Day-to-day use of new system | Low | High | Support | Inform | Conduct demos & feedback sessions, early UAT
External Customers | Place orders via the platform | Low | High | Support | Inform | Pre-launch announcement, portal tutorials, feedback surveys
Stakeholder: Enter the names of the project stakeholders
Stakeholder's Role: Enter the stakeholders role in the project
Influence High/Low: Use the dropdown box to enter the stakeholders level of influence in the project (Select High or Low)
Interest High/Low: Use the dropdown box to enter the stakeholders level of interest in the project (Select High or Low)
Monitor, Inform, Satisfy or Manage: Use the dropdown box to select an approach for the stakeholder based on their level of influence and level of interest: - High influence/High interest: Manage by fully engaging them in the process - High influence/Low interest: Satisfy with levels of communication necessary to meet their needs - Low influence/Low interest: Monitor for changing needs and interests - Low influence/High interest: Inform with appropriate levels of communication to safeguard against issues
Strategy: Enter a strategy action based on the selection of monitor, inform, satisfy, or manage
Strategy Owner: Enter a strategy action owner
Strategy Date: Enter a strategy action date
Comments: Enter necessary comments based on the stakeholder line item
Note on G5: High influence/High interest: Manage by fully engaging them in the process High influence/Low interest: Satisfy with levels of communication necessary to meet their needs Low influence/Low interest: Monitor for changing needs and interests Low influence/High interest: Inform with appropriate levels of communication to safeguard against issues